## Sheet1
Task | Timeframe | Assignee | Status
Mgmt frames through data path | Before qca_main checkin
OS Shim hookup to new data path TxRx | Before basic ping | doug | complete
Port toba host data path fixes (Not a cleanup) | Before emulation stress tests |  | complete
FW_IDX management by target (eventual design) | Before chatter packet feature implementation
Valid implementation for adf_os_malloc_consistent | Before emulation bring up | nick | complete
Provide a valid osdev_t object to adf_nbuf_map_single | Before emulation bring up | nick | complete
Cleanup host interest area and other configuration for data path parameters | Before sampling | srinivas | complete
Replace adf_nbuf_map_single with a revised version of adf_nbuf_map (not single) | before porting to OS with multiple fragments per netbuf |  | complete
Add mutex to tx operations | Before emulation stress tests | nick | complete
Add mutex to rx operations | Before emulation stress tests | nick | complete
Add mutex to peer_detach operation | Before emulation stress tests | nick | complete
Allow multiple peer IDs to be stored per peer | Before emulation stress tests | nick | complete
Fix bug of calling htt_rx_ring_refill_n too early and too often. |  | doug | complete
Make osif_deliver_data accept a linked list of nbufs rather than just a single. | Before emulation stress tests | doug | complete
Document that HTCSendDataPkt can accept a linked list of netbufs. (Fix it if it can't.) | Before HL data bringup
Document that HIFSend_head can accept a linked list of netbufs. (Fix it if it can't.) | Before HL data bringup
Provide a per-fragment endianness conversion flag in the adf_nbuf ADT (and the linux version of adf_nbuf) | Before db120 bringup | doug? | complete
Set endianness conversion flag for each netbuf fragment in HTT. | Before db120 bringup | doug? | complete
Use the endianness conversion flag in hif/new_pci to set the per source element CE endianness correction flag. | Before db120 bringup | doug? | complete
Don't process non-EAPOL data frames until authenticated | Before sampling |  | in progress (part of FW rx desc)
Add pdev pause / unpause to ctrl --> txrx API (for HL) | Before WDI API finalization | doug | complete
Add security-type spec to ctrl --> txrx API (for PN check configuration). | Before PN check feature implementation |  | in progress (part of rx defrag)
FW periodically reads actual value of host's FW_IDX shadow register | Before emulation stress tests | nick? | complete
Check if the download size for management tx frames is set correctly. | Before qca_main checkin(?)
Add HL version of HTT rx descriptor access methods, and allow LL versus HL version to be selected either statically or dynamically. | Before HL data bringup
Clean out irrelevant elements from host's peer ID FIFO during ol_txrx_peer_detach | Before emulation stress tests | doug | complete | peer ID FIFO no longer needed, after peer attach/detach redesign
Handle non-success (no response, dropped) status for tx completion message | Before sampling and before HL emulation stress tests (depends on FW changes)
Store copy of high-latency / low-latency configuration flag inside txrx and htt pdev objects, rather than repeatedly querying ol_cfg_is_high_latency(). | Before host CPU profiling and optimizations |  | complete | "is_high_latency" flag added to htt pdev. N/a to txrx, where this function is not used in the fast path.
Store copy of ol_cfg_rx_fwd_inter_bss configuration flag inside txrx pdev object, rather than repeatedly calling the ol_cfg function. | Before host CPU profiling and optimizations |  | n/a | The forwarding logic has been moved to the target as part of the FW rx desc changes.
Optimize the htt_tx_desc_init macro to just set the words to the appropriate values (bit-or of shifted field values), rather than setting the word to zero and then doing a separate bit-or for each field within the word. | Before host CPU profiling and optimizations
Do endianness byte-swap when storing the tx fragment addresses into the HTT tx descriptor. (TBD: does the PPDU tx descriptor tell the HW what endianness to use? If so, then this task is not required.) | Before db120 bringup | nick | complete
Do optional endianness byte-swap when storing the rx buffer addresses into the HTT rx ring. (Don't do byte swap even on big-endian host, if the FW is reading the ring via CE.) (TBD: Does the HW have a global endianness setting it uses for rx MAC DMA addresses? If so, this step may not be required.) | Before db120 bringup | nick | complete
Fix how HIFSend_head rejections from HTCIssuePackets are handled - when HTCIssuePackets calls SendPacketCompletion, which calls DoSendCompletion, which uses the EpTxComplete callback, HTC needs to check whether the packet was successfully downloaded, and if not, delete the tx frame as well as the HTC packet. Alternatively, HTC should just requeue the packets to the endpoint TxQueue, so they will be tried again eventually. | Before emulation stress tests | doug | complete
Use a MSDU rx descriptor flag to determine if DA is mcast/bcast, rather than directly checking the DA within the netbuf payload. | After FW rx descriptor fields are added; before productization. |  | n/a | The forwarding logic has been moved to the target as part of the FW rx desc changes.
Handle multi-cast echo filtering for proxy-STA case | before productization |  | n/a | The multicast echo logic has been moved to the target as part of the FW rx desc changes.
Avoid using hw_rx_desc_base for HTT host rx ring descs, to avoid allocating mem for unused ppdu_start and ppdu_end descriptors. | before productization | nick | complete
Change HTT_RX_BUF_SIZE to be a formula (sizeof(hw rx desc) + align pad + sizeof(fw rx desc) + align pad + max MSDU size) rather than a hard-coded constant. | before productization
Remove the flags_pending flag from the tx_desc struct, and instead use tx_desc->ref_cnt to determine whether the tx desc needs to be deallocated during pdev_detach | before productization |  | complete
If htt_tx_send_std returns an error, have ol_tx_send return the tx frame to the OS shim, rather than freeing it. | before productization
Add a timer to retry htt_rx_ring_fill_n if the host isn't able to allocate enough buffers to keep the ring full. (Otherwise, there could be a data deadlock, where due to the rx ring being emptied, htt_rx_ring_fill_n is never called.) | before productization